## Task List
No | Task | Deadline | Status | Note
Before Winter Break
1 | Select group's main contact point to communicate with supervisor and clients | 2022-11-21 | Done | Tom
2 | Formulate set of questions for the clients | 2022-11-22 | Done | Based on Group project plan template/Ethic form - information to define scope/objective/timescale - what data is available, in what format, and how you can access this data - requirements of the project - what the organisation expects from the project - type of support that they can offer ex. who will respond to your queries? What is their availability? How often can you communicate with them? Will there be future meetings? *It is important that all stakeholders agree on a timescale and milestones of the key phases of the project
3 | Share questions with supervisor | 2022-11-24 | Done
4 | Arrange meeting with supervisor | 2022-11-24 | Done
5 | Get the approval for questions from supervisor | Tentatively 24-Nov-22 | Done
6 | Email to client to introduce themselves, share questions and arrange a meeting | Tentatively 25-Nov-22 | Done
7 | Arrange a meeting between all stakeholders to discuss the questions and any other business | Tentatively 28-Nov-22 | Done | meet 15 min before client meeting and 30 mins after
8 | Send signed contract document to PLN by email | 2022-12-02 | Done
9 | Send draft of Group Project Plan (using group project plan template) and Ethic Form to supervisor to get feedback | 2022-12-05 | Done | Group project plan - Reviewed (24-Jan-23)
After Winter Break
1 | Ensure that Group Project Plan has been signed by all stakeholders | 2023-01-23 | Done
2 | Ensure that Ethic Form has been signed by the academic supervisor | 2023-01-23 | Done
3 | Submit 500-word Group Project Plan on BB (along with ethic form) | 2023-01-26 | Done | 10%
4 | Deep work on project (Detailed tasks will be listed out later) | 2023-02-27 | Not started
5 | Share early version of Group Project Report and Presentation to supervisor | 2023-03-06 | Not started
6 | Submit 2000-word final version of Group Project Report on BB (along with contribution statement for peer assessment) | 2023-03-23 | Not started | 30%
7 | Submit 10-minute final version of Group Project Presentation on BB | 2023-03-23 | Not started | 20%
8 | Submit 2000-word Applied Research Project proposal - individual work on BB | 2023-05-04 | Not started | 40%

## Sheet1 (hidden)
Not started
In progress
Done
Cancelled

## Key Inquiry List
No | Inquiry | Response | Action Item | Action Owner | Remark | Status

## Draft Inquiry List
Inquiry Tracking Sheet for LOQBOX
No | Session Name | Inquiry | Order | Expected Respondent | Response | Action Item | Action Owner | Remark | Status
1 | 1st Meeting with Supervisor | Can you share information about project in details? |  | Supervisor
2 | 1st Meeting with Supervisor | Should we complete all works/implementations by 27-Feb or continue working after 27-Feb? |  | Supervisor
3 | 1st Meeting with Supervisor | How many meetings that we could have with the client before submit the draft of proposal? |  | Supervisor
4 | 1st Meeting with Supervisor | Anything that we should know before meeting with the client? |  | Supervisor
5 | 1st Meeting with Supervisor | Any particular knowledge or area that we should research before meeting with the client/starting the project? |  | Supervisor
6 | 1st Meeting with Supervisor | Any concern if our team propose to catch up with you and client fornigthly? (Client first |  | Supervisor
7 | 1st Meeting with Supervisor | Can you please sharer your available timeslots for next year to us? (Jan-Mar) |  | Supervisor
8 | 1st Meeting with Client | [Business case] Can you share the information about your business? | 1 | Client |  | Send pre-meeting |  | Financial well being company - helps people about financial Example products LOQBOX save - increase credit scores + saving US, India
9 | 1st Meeting with Client | [Business case] What is the problem that you are having? |  | Client |  |  |  | Membership - paid tier (get access to all LOQBOX products), free tier can upgrade and downgrade Want to know the reasons why people choose to downgrade to free tier -- anything we can learn from this (Don't have time and resource to work in data analytic field) - Have data over a year since products were launch -- export text/string from database + timestamp - Can share sample data by this week (after getting green ligth)
10 | 1st Meeting with Client | [Business case] Why do you need this project?/What is the objetive of this project? |  | Client |  |  |  | Previous work : No
11 | 1st Meeting with Client | [Previous work] Have you tried any form of data/text analytics before? If yes - What is the methodology that you use before to analyse text? - Who is the key person in the previous implementation? - Is there any problem/blocker from the previous implementation? If no - What is the constraint? | Follow-up | Client |  | Asking during meeting
12 | 1st Meeting with Client | [Output] What is the expected outcomes from this project? | 3 (data and ideal results) | Client
13 | 1st Meeting with Client | [Output] How to measure whether this project is success or not? |  | Client
14 | 1st Meeting with Client | [Output] Which particular areas that you want to improve from this project? (ex. Finance, Customer service etc.) |  | Client
15 | 1st Meeting with Client | [Output] Can you share about the requirements of this project in details? |  | Client |  |  |  | It might be too much details in this stage
16 | 1st Meeting with Client | [Justification] How this project can help you solve the problem? | 2 | Client
17 | 1st Meeting with Client | [Justification] How will text data help us find a solution to your problem? |  | Client |  |  |  | Why are they focusing on text mining?
18 | 1st Meeting with Client | [Project timeline] What date/period that you expect the project will be end? | 4 (present rough guideline) | Client |  |  |  | Can come up with generic timeline/ Come up with very high level timeline in order to manage clients' expectation
19 | 1st Meeting with Client | [Project timeline] What are the deliverables you expect from our group at the end of the project(ex. Report etc.)? |  | Client
20 | 1st Meeting with Client | [Project timeine] What are the key activities that you expect to have during development/implementation period(ex. Demo run, Checkpoint)? |  | Client
21 | 1st Meeting with Client | [Dependency] Do you have any constraints for the project (ex. Budget, Resource etc.)? | Follow-up question concerning the resources they will be able to offer us. ie. how can they support us? | Client
22 | 1st Meeting with Client | [Communication Plan] To confirm - Sam Hunt is the contact point for our group. Is there any other person to provide support when we have further questions? | towards the end of the meeting as a follow-up | Client |  |  |  | Fornightly meeting Company contact point : Sam Hunt - Head of Finance, Jamie - Data analyst
23 | 1st Meeting with Client | [Communication Plan] How often do you expect to have a meeting with our group? What day/time do you prefer to have a meeting? Who are required to attend a meeting? |  | Client
24 | 1st Meeting with Client | [Data] What kind of data will you provide(ex. Text, Image)? | follow-up from 3 and then in a few weeks will have more Q's | Client |  |  |  | In this stage, we should focus on what are the data that they have and when will they can provide.
25 | 1st Meeting with Client | [Data] What is the format of provided data(ex. ? |  | Client
26 | 1st Meeting with Client | [Data] What are the sources of data? |  | Client |  |  |  | First meeting should focus on introduce ourselves and pick up the key information to shape the project plan
27 | 1st Meeting with Client | [Data] How to access the data? |  | Client
28 | 1st Meeting with Client | [Data] How long will you provide us to access the data? |  | Client
29 | 1st Meeting with Client | [Data] What is the earliest date that you can provide data to us? |  | Client
30 | 1st Meeting with Client | [Data] Do we need to assess the data to generate text mining? |  | Client
31 | 1st Meeting with Client | [Data] To confirm - the provided data is anonymised |  | Client
32 | 1st Meeting with Client | [Data] Briefly describe your data. (e.g type of sample, sample size, level of aggregation (individual, city, county, state…), main variables or other relevant information. |  | Client
33 | 2nd Meeting with Client | [Data] Clarification of what the change of options implies. |  | Client
34 | 2nd Meeting with Client | [Data] Clarification required of the importance of the ‘notes’ to the project. |  | Client
35 | 2nd Meeting with Client | [Data] If a customer has more than one option activated are they downgrading all of them? |  | Client
36 | 2nd Meeting with Client | [Data] If a customer only has save activated were they a paying customer in the first place? |  | Client
37 | 2nd Meeting with Client | [Data] Some customers have more than one chosen reason for why they downgraded, what does this mean? |  | Client
38 | 2nd Meeting with Client | [Data] To double check – if a customer upgrades and then downgrades straight away they are not charged. Is this right? |  | Client
39 | 2nd Meeting with Client | [Data] Do Loqbox charge weekly, monthly or annually? | Follow-up: If someone downgraded would they still have access for the time they’ve paid for? | Client
40 | 2nd Meeting with Client | [Data] There are 472 obs which have reasons but no values; does this mean it is a ‘note’? |  | Client
41 | 2nd Meeting with Client | [Data] Row 73 – why are all values 0? What does this mean? |  | Client
42 | 2nd Meeting with Client | [Data] Rows 23+55: what is the difference between these two reasons? |  | Client
0

## Contact list
Name | Team | Email
Sam Hunt | Head of Finance | sam@loqbox.com
jamie.mcilveen@loqbox.com
Matthew Higgs | Academic Supervisor | matthew.higgs@bristol.ac.uk
Matthew Higgs | Academic Supervisor | qz21101@bristol.ac.uk
Danie Nguyen | Group Member | danie.nguyen.2022@bristol.ac.uk
Jiayi Liu | Group Member | ug22038@bristol.ac.uk
June Chukiatthakoeng | Group Member | uv22151@bristol.ac.uk
Matthew Baber | Group Member | ih22917@bristol.ac.uk
Noon Chompoonuch | Group Member | jt22215@bristol.ac.uk
Tom Pannell | Group Member | xi19799@bristol.ac.uk

## List (hidden)
Status Type | Meaning | KTB/ACN
Open | Action not start yet | KTB
In-progress | Wait for response | ACN
Overdue | Exceed due date | KTB &ACN
Closed | Received response